## Gantt Chart w % Complete
* = an automatically calculated cell
| TASK NAME | START DATE | DAY OF MONTH* | END DATE | DURATION* (WORK DAYS) | DAYS COMPLETE* | DAYS REMAINING* | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 5 | 2018-01-08 | 4 | 0 | 4
| Approve Page Copy | 2018-01-08 | 8 | 2018-01-11 | 4 | 0 | 4
| Review Landing Page Design | 2018-01-11 | 11 | 2018-01-16 | 6 | 0 | 6
| Build Landing Page | 2018-01-14 | 14 | 2018-01-19 | 6 | 0 | 6
| Code Review Landing Page | 2018-01-17 | 17 | 2018-01-23 | 7 | 0 | 7
Second Sample Project
| Write Promotional Email | 2018-01-09 | 9 | 2018-01-12 | 4 | 0 | 4
| Design Promotional Email | 2018-01-12 | 12 | 2018-01-19 | 8 | 0 | 8
| Send Promotional Email | 2018-01-17 | 17 | 2018-01-19 | 3 | 0 | 3
| Analyze Campaign Results | 2018-01-22 | 22 | 2018-01-26 | 5 | 0 | 5
Third Sample Project
| Plan Agenda for Meeting | 2018-01-15 | 15 | 2018-01-19 | 5 | 0 | 5
| Reserve Room | 2018-01-22 | 22 | 2018-01-23 | 2 | 0 | 2
| Finalize Presentation | 2018-01-22 | 22 | 2018-01-26 | 5 | 0 | 5
| Approve Presentation | 2018-01-26 | 26 | 2018-01-29 | 4 | 0 | 4
| Create Invitations | 2018-01-22 | 22 | 2018-01-25 | 4 | 0 | 4
Fourth Sample Project
| Rewrite Online Calculator | 2018-01-15 | 15 | 2018-01-24 | 10 | 0 | 10
| Code Review Calculator | 2018-01-25 | 25 | 2018-01-30 | 6 | 0 | 6
| Update Messaging | 2018-01-24 | 24 | 2018-01-30 | 7 | 0 | 7
| Publish Calculator | 2018-01-30 | 30 | 2018-01-31 | 2 | 0 | 2
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1

## Basic Gantt Chart
Euan Mendoza Class Manager Project Gantt Chart
* = an automatically calculated cell
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS)
Project Setup
| Setup Go Dev Server | 2019-04-01 | 2019-04-03 | 0 | 3
| Setup Javascript Stack | 2019-04-04 | 2019-04-07 | 3 | 4
| Setup Database | 2019-04-08 | 2019-04-11 | 7 | 4
| Connect Database with Server | 2019-04-12 | 2019-04-14 | 11 | 3
| Authentication, hashing and encryption | 2019-04-15 | 2019-04-18 | 14 | 4
| GraphQL API | 2019-04-02 | 2019-04-19 | 1 | 18
Frontend Development
| Landing and sign in pages | 2019-04-17 | 2019-04-20 | 16 | 4
| Dashboard and Class pages | 2019-04-21 | 2019-04-25 | 20 | 5
| Rich Text Editing | 2019-04-26 | 2019-04-30 | 25 | 5
| Routing | 2019-04-17 | 2019-05-01 | 16 | 15
| Apollo GraphQL integration | 2019-04-17 | 2019-05-02 | 16 | 16
Testing and First Solution Evaluation
| Unit Testing | 2019-05-03 | 2019-05-08 | 32 | 6
| GraphQL Playground Testing | 2019-05-09 | 2019-05-11 | 38 | 3
| User Interface testing | 2019-05-12 | 2019-05-15 | 41 | 4
| First Evaluation | 2019-05-16 | 2019-05-18 | 45 | 3
Emergency Buffer Period, Bug Fixes, Final Evaluation and Deployment
| Bug Fixes | 2019-05-19 | 2019-05-23 | 48 | 5
| Final Evaluation | 2019-05-24 | 2019-05-27 | 53 | 4
| Deployment/Documentation | 2019-05-28 | 2019-06-03 | 57 | 7
| Buffer Period | 2019-05-28 | 2019-06-07 | 57 | 11
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1

## Manual Chart
GANTT CHART TEMPLATE
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 2 | Nathan | 100%
|  |  |  | 0 | Meredith | 80% | bar: WEEK 2 M to WEEK 2 T
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 4 | Brandon | 60% | bar: WEEK 1 F to WEEK 2 Th
| Build Landing Page | 2018-01-14 | 2018-01-19 | 5 | Michael | 40% | bar: WEEK 2 T to WEEK 3 M
| Code Review Landing Page | 2018-01-17 | 2018-01-21 | 3 | Rachel | 20% | bar: WEEK 2 Th to WEEK 3 W
| Promote Landing Page | 2018-01-20 | 2018-01-23 | 2 | Annie | 10% | bar: WEEK 3 T to WEEK 3 Th
Second Sample Project
| Write Promotional Email | 2018-02-05 | 2018-02-08 | 4 | Nathan | 100%
| Design Promotional Email | 2018-02-08 | 2018-02-13 | 4 | Meredith | 80%
| Send Promotional Email to Contacts | 2018-02-11 | 2018-02-16 | 5 | Michael | 60%
| Analyze Results of Email Campagin | 2018-02-14 | 2018-02-23 | 8 | Annie | 40%
Third Sample Project
| Plan Agenda for Team Meeting | 2018-03-05 | 2018-03-08 | 4 | Rachel | 100%
| Reserve Room and Resources for Meeting | 2018-03-08 | 2018-03-13 | 4 | Michael | 80%
| Finalize Team Presentation | 2018-03-11 | 2018-03-16 | 5 | Brandon | 60%
| Review & Approve Presentation | 2018-03-14 | 2018-03-19 | 4 | Meredith | 40%
| Create Invitations for Meeting | 2018-03-17 | 2018-03-21 | 3 | Annie | 20%
| Setup Room for Meeting | 2018-03-20 | 2018-03-25 | 4 | Nathan | 10%
Fourth Sample Project
| Rewrite Code for Online Calculator | 2018-04-05 | 2018-04-08 | 2 | Nathan | 100%
| Code Review Updated Calculator | 2018-04-08 | 2018-04-10 | 2 | Meredith | 80%
| Update Messaging for Calculator | 2018-04-11 | 2018-04-16 | 4 | Michael | 60%
| Publish New Calculator to Site | 2018-04-14 | 2018-04-18 | 3 | Rachel | 40%
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])